## Sheet1
Week | Day | Date | Task | Status | Overall | On Track
Week 1 | Day 1 | 2025-01-15 | Define project scope and core features. | Done
Week 1 | Day 2 | 2025-01-16 | Set up project repository and initialize Node.js application.
Week 1 | Day 3 | 2025-01-17 | Install dependencies (Express, Mongoose, etc.) and set up folder structure.
Week 1 | Day 4 | 2025-01-18 | Implement Company schema and API endpoints for company creation.
Week 1 | Day 5 | 2025-01-19 | Implement User schema and API endpoints for user management.
Week 1 | Day 6 | 2025-01-20 | Integrate `passport` for authentication and test user login functionality.
Week 1 | Day 7 | 2025-01-21 | Test and refine company and user management workflows.
Week 2 | Day 8 | 2025-01-22 | Design database schema for Objectives and Key Results.
Week 2 | Day 9 | 2025-01-23 | Implement API endpoints for creating, retrieving, updating, and deleting Objectives.
Week 2 | Day 10 | 2025-01-24 | Implement API endpoints for creating, retrieving, updating, and deleting Key Results.
Week 2 | Day 11 | 2025-01-25 | Add validation to ensure Key Result dates align with Objective dates.
Week 2 | Day 12 | 2025-01-26 | Build basic frontend forms for company and user management.
Week 2 | Day 13 | 2025-01-27 | Build frontend forms for OKR creation and management.
Week 2 | Day 14 | 2025-01-28 | Test and refine OKR management features.
Week 3 | Day 15 | 2025-01-29 | Integrate Microsoft Graph API for fetching meeting recordings.
Week 3 | Day 16 | 2025-01-30 | Download and process recordings (audio extraction if needed).
Week 3 | Day 17 | 2025-01-31 | Integrate Whisper for audio-to-text transcription.
Week 3 | Day 18 | 2025-02-01 | Store transcriptions in the database and associate with meeting notes.
Week 3 | Day 19 | 2025-02-02 | Build API endpoints for meeting notes management.
Week 3 | Day 20 | 2025-02-03 | Add manual tagging of meeting notes to Objectives.
Week 3 | Day 21 | 2025-02-04 | Test end-to-end meeting notes management.
Week 4 | Day 22 | 2025-02-05 | Integrate Hugging Face models for summarization of meeting notes.
Week 4 | Day 23 | 2025-02-06 | Develop a feature to auto-suggest Objectives for meeting notes.
Week 4 | Day 24 | 2025-02-07 | Build frontend forms for meeting notes and tagging.
Week 4 | Day 25 | 2025-02-08 | Develop and test reminders for pending tasks using Nodemailer.
Week 4 | Day 26 | 2025-02-09 | Build a chatbot feature for detecting non-SMART Key Results.
Week 4 | Day 27 | 2025-02-10 | Test and refine chatbot interactions.
Week 4 | Day 28 | 2025-02-11 | Finalize frontend for meeting notes and OKR integration.
Week 5 | Day 29 | 2025-02-12 | Perform system-wide testing of all features.
Week 5 | Day 30 | 2025-02-13 | Optimize backend queries for performance.
Week 5 | Day 31 | 2025-02-14 | Fix bugs and refine UI/UX for all features.
Week 5 | Day 32 | 2025-02-15 | Test integration of reminders and email notifications.
Week 5 | Day 33 | 2025-02-16 | Prepare a staging environment for deployment testing.
Week 5 | Day 34 | 2025-02-17 | Conduct load testing and resolve performance issues.
Week 5 | Day 35 | 2025-02-18 | Test role-based access control for company and user management.
Week 6 | Day 36 | 2025-02-19 | Deploy the application to a cloud platform (e.g., Render, Heroku).
Week 6 | Day 37 | 2025-02-20 | Conduct a walkthrough with test users and gather feedback.
Week 6 | Day 38 | 2025-02-21 | Refine features based on user feedback.
Week 6 | Day 39 | 2025-02-22 | Write and organize documentation for setup and usage.
Week 6 | Day 40 | 2025-02-23 | Prepare a demo presentation for stakeholders.
Week 6 | Day 41 | 2025-02-24 | Conduct final testing and ensure readiness for launch.
Week 6 | Day 42 | 2025-02-25 | Launch the MVP and monitor for early issues.
Week 6 | Day 43 | 2025-02-26 | Gather post-launch feedback from initial users.
Week 6 | Day 44 | 2025-02-27 | Plan for additional features and future iterations.
Week 6 | Day 45 | 2025-02-28 | Celebrate the successful launch of the MVP!